## Sheet1
Task | Assigned To | Start Date | End Date | Duration (days) | Expertise needed
Team setup and infrastructure check | Yacine | 2025-05-30 | 2025-06-15
Standardised templates for extraction | Yacine | 2025-05-30 | 2025-06-15
Literature review data extraction | Afrouz | 2025-05-30 | 2025-06-26
EM-DAT extraction and processing | Afrouz | 2025-05-30 | 2025-06-27
Social/media data extraction (social, news, web) | Andrie | 2025-06-06 | 2025-06-20
Citizen assemblies (organise and analyse) | Lisa | 2025-06-30 | 2025-07-14
provide an inventory of social media public sources/ URLs/Open access previous projects | larisa, Bratislava, Odesa, thessaloniki | 2025-06-13 | 2025-06-20
Identify institutions that have/maintain social media data | Larisa, Bratislava, Odesa, thessaloniki | 2025-06-13 | 2025-06-20
Provide data local authority data gathering (AHEPA) | AHEPA | 2025-06-13 | 2025-07-14
Provide data local authority data gathering (Odesa) | Odesa | 2025-06-13 | 2025-07-14
Provide data local authority data gathering (Bratislava) | Bratislava | 2025-06-13 | 2025-07-14
Provide data local authority data gathering (Larisa) | Larisa | 2025-06-13 | 2025-07-14
Social Media Processing & Triangulation (NLP, filtering, tagging) | Andrie | 2025-06-21 | 2025-07-15
Pilot test on sample data | Open | 2025-07-15 | 2025-07-17 |  | Data engineer or data scientist
Data Harmonisation and Event Preprocessing (all sources) | Open | 2025-07-17 | 2025-07-20 |  | GIS specialist or geospatial analyst or data scientist
Multi-source integration + confidence scoring | Open | 2025-07-20 | 2025-07-25 |  | Data Scientist
Qualitative and quantitative synthesis | Open | 2025-07-25 | 2025-07-31 |  | Qualitative researcher (NVivo/Atlas.ti, grounded theory)
Interdependency analysis (networks, models) | Open | 2025-07-31 | 2025-08-06 |  | Network analyst or system modeler(Familiarity with tools like Gephi, Vensim, or causal modelling frameworks)
Event mapping (GIS, metadata tagging) | Open | 2025-08-06 | 2025-08-11 |  | GIS analyst (QGIS, ArcGIS, or Python with GeoPandas/PostGIS)
Validation + stakeholder feedback | Yacine | 2025-08-12 | 2025-08-14
Final documentation and delivery | All | 2025-08-14 | 2025-08-28