Antifragicity

Minutes of the WP2 Meeting

Friday 24 October 2025 - 13:00 – 14:00

- Attendance:

- Yacine Rezgui, Ali Ghoroghi, Afrouz Ghaemi, Lisa Verhasselt, Sun Linghang, Katerina Moschopoulou, Qiaosen Li, Cristina De Nardi, Antonis Sapountzis, Anastasia Tzioutziou, Zhaoxing Wang, Marianna Páleníková, Michail Makridis, Natalia Horshkova

- Meeting Summary

T2.2 – Citizen Assemblies (LV)

- Website nearing launch; translations: Bratislava complete, Thessaloniki pending; Larissa provisionally scheduled.

- Data Protection Officers engaged; approvals expected next week; recruitment to begin post-approval.

- “Your Voice Matters” online input to mirror forum questions; live-streaming not recommended due to security concerns and GDPR and best practice; consider posting selected expert presentation recordings with consent.

- Accessibility features (contrast, dark mode, text size) being added to the website; Bratislava requests immediate Slovak materials online to align with paid ads.

T2.3 – Equilibrium Model (AG)

- Deliverable D2.3 completed and reviewed; submission to portal will be timed closer to deadline; AG to develop a publication draft and circulate per consortium agreement.

T2.4 – Social Acceptability Survey

- Survey structure ready; awaiting citizen-forum outputs for item integration; alignment meeting held on SUMO app integration, action considered closed. Tanslation timeline is being planned for November

T2.5 – Ontology (AFG)

- Requirement templates requested from all pilot cities; several still pending; deadline agreed as Friday 31 October 2025.

- AFG to synthesise city requirements with D2.1 and literature; will circulate consolidated set and competency-question list for partner input.

T2.6 – Delphi Consultation (AG)

- 13 expert nominations received; need additional nominees in Circular Economy and Urban Resilience to balance domains; target ≈40 experts.

- Partners reminded to send names, institutions, emails, and domains; Follow-ups ongoing with NTUA and pilot cities.

T2.7 – KPIs & Dashboard (MT)

- Scoping review underway (~65 academic sources plus EU projects and international reports); content analysis commencing; land-use indicators to be mapped across economic/social/environmental themes.

Literature Reviews

- Bottom-up (KM): Progress slow until November; LV and TV reiterated support and asked KM to share with the small group to accelerate drafting.

- Top-down (AFG): Submission targeted before end of October.

- Action Items:

- WP2-A1: LV to coordinate DPO contacts and schedule per-site meetings next week for T2.2 practicalities.

- WP2-A2: D2.3 will be submitted after review by YR by end of Oct.

- WP2-A3: Antonis + demo-sites to finalise website sections, enable accessibility tools, and activate “Your Voice Matters” by 31 Oct 2025.

- WP2-A4: LV/Comms to publish Slovak materials immediately and confirm Thessaloniki translations by 31 Oct 2025.

- WP2-A5: AG to develop 3–5 equilibrium teaser/quiz questions for LinkedIn engagement campaign and send to Antonis by 29 Oct 2025.

- WP2-A6: AFG to collect ontology requirement templates from all cities and circulate consolidated set + competency questions by 31 Oct 2025.

- WP2-A7: All partners to nominate 3–4 Delphi experts (name, institution, email, domain), prioritising Circular Economy & Urban Resilience, by 31 Oct 2025.

- WP2-A8: LV/AUTH to integrate SUMO-aligned content into T2.4 survey as citizen-forum outputs arrive; plan translation workflow for Nov 2025.