Antifragicity

Minutes of the WP2 Meeting

Friday 26 September 2025 - 9:00 – 10:00

- Attendance:

- Yacine Rezgui, Ali Ghoroghi, Evangelos Manthos, Sun Linghang, Marianna Páleníková, Afrouz Ghaemi, Theocharis Vlachopanagiotis, Anastasia Tzioutziou, Andrei Hodorog, Zhaoxing Wang, Natalia Horshkova, Katerina Moschopoulou, Maria Tsami

- Meeting Summary

Meeting Time Change (YR):

- Due to teaching commitments, It is proposed moving meetings from Friday mornings to another day. Partners agreed to circulate a Doodle poll to find an alternative slot.

Task 2.2 – Citizen Assemblies:

- Activities progressing as planned, despite some deviations; update to be reported to the PO. Assemblies expected to proceed in pilot cities.

Task 2.3 – Equilibrium Model (AG):

- AG presented the revised convergence-based model, incorporating partner feedback. Introduced division of positive/negative KPIs, behavioural parameter, and hybrid calibration (expert elicitation + data-driven).

- Plan to prepare three-layer equilibrium following discussion with MT, AT and SLS. Deliverable draft to be sent to reviewers by 7 October; feedback expected within two weeks; submission by end of October.

- Reviewers confirmed: Maria Tsami, Anastasia Tzioutziou.

Task 2.4 – Requirements:

- Survey emphasised as critical. Update expected next week.

Task 2.5 – Ontology (AFG, ZW):

- AFG presented detailed methodology and timeline: requirement capture (by 6 Oct), synthesis and reuse scan (by 29 Oct), competency questions and Delphi validation (by 14 Nov), ontology modelling, and use-case development (Nov–Dec).

- Partners asked to complete requirement templates and nominate contact points.

- Discussion raised by MT and AT: need for extended time and possible external input on use-case validation. YR suggested adding continuous improvement loop as a fifth stage.

- WP5 (ZW) raised questions on middleware and integration; a joint meeting with Cardiff, ETH, ROI, and DEMO to be organised.

Task 2.6 – Delphi Consultation (YR, AFG):

- Aim: expert validation of requirements leading into use-case development.

Task 2.7 – KPIs & Dashboard (EM):

- EM confirmed invitation circulated; Thessaloniki team preparing initial plan for presentation next week.

WP3 Data (EM, MP):

- Partners reminded to complete Excel data file for WP3.

- EM reported progress on agreements with AHEPA and clarification of data availability.

- MP confirmed requested dataset exists in DMP; licensing and delivery being arranged.

General Assembly (MP):

- Scheduled for December in Bratislava; venue booked.

- Basic facilities (projector, screen) confirmed; hotel options shared.

- Partners encouraged to arrange travel soon; participation from Odesa expected if feasible.

- Action Items:

- WP2-A1: AG to circulate revised equilibrium model to reviewers (MT, AT) by 7 October.

- WP2-A2: All partners to complete Doodle poll to reschedule weekly meeting.

- WP2-A3: AFG to circulate requirement template; partners to submit by 6 October and nominate contact points.

- WP2-A4: Organise joint WP2–WP5 meeting (Cardiff, ETH, ROI, DEMO) to clarify middleware and ontology integration.

- WP2-A5: Thessaloniki team to present initial KPI/dashboard plan in next week’s meeting.

- WP2-A6: Partners to complete WP3 Excel data file promptly; MP to resolve licensing issues.

- WP2-A6: MP to continue preparations for December General Assembly and share updated logistics.