Antifragicity

Minutes of the WP2 Meeting

Friday 7 November 2025 - 13:00 – 14:00

- Attendance:

- Yacine Rezgui, Ali Ghoroghi, Afrouz Ghaemi, Li Qiaosen, Tania Demirtzioglou,

- Cristina De Nardi, Zhaoxing Wang, Lisa Verhasselt, Marianna

- Páleníková, Evangelos Manthos, Linghang Sun, Maria Tsami, Natalia Horshkova

- Meeting Summary

General Assembly Logistics (MP)

- • Only 16 out of ~20 invitees confirmed attendance; all partners requested to confirm presence via calendar invitation for accurate logistics planning.

- • Social event evening arrangements discussed; partners will split costs individually and seek reimbursement from their institutions.

- • Transport department representatives (1-2 people) from Bratislava requested attendance to better understand project scope and deliverables; AG to circulate email to all partners for approval.

T2.2 – Citizen Assemblies (LV)

- • Slovak translations submitted to Austrado; website updates pending in Slovak and Greek.

- • Bratislava survey responses: 244 responses received.

- • Data protection agreements require urgent completion; demo sites (Bratislava excluded as already completed) must sign agreements to enable registration survey launch. Already ~2 weeks behind schedule.

- • Larissa engagement challenges persist; limited responsiveness from Larissa contacts causing delays in citizen forum planning and deliverables.

T2.3 – Equilibrium Model

- • D2.3 successfully submitted.

T2.4 – Social Acceptability Survey

- • No substantive updates; survey launch awaits citizen forum outputs for integration.

T2.5 – Ontology (AFG)

- • All city requirements gathered except Larissa (no response received).

- • Competency questions and use cases from partners still outstanding; deadline Monday 10 November 2025.

- • Consultation phase must complete by 14 November 2025; deliverable due end of January 2026.

Bratislava Data Sharing Discussion (MP/LS)

- • Transport department cautious about sharing VISUM model data; 5 meetings held to date.

- • Concerns raised: (1) potential commercial exploitation of data, (2) ETH Zurich potential involvement in upcoming Slovakia transport model tender.

- • Linghang to verify ETH institute's tender participation plans and report back to enable data sharing resolution.

- • Transport department attendance at GA could facilitate in-person data discussions and relationship building.

T2.6 – Delphi Consultation

- • 14 expert nominations received; awaiting submissions from NTUA and pilot cities.

- • Evangelos to send reminder emails to NTUA for outstanding nominations.

T2.7 – KPIs & Dashboard (AUTH)

- • Task 2.7.1 nearing completion; team divided work into 3 subtasks.

- • Ongoing literature and content analysis to develop final dashboard indicator catalogue.

- • Progress update expected next week on Task 2.7.1 conclusions.

WP7 Coordination (YR/TD)

- • D7.2 discussed; meeting scheduled with project officer Friday morning to clarify deliverable approach.

- • Proposed solution: create light deliverable indicating key exportable results from proposal, maintaining as living document until WP formally commences.

- Action Items:

- WP2-A1: All partners to confirm General Assembly attendance via calendar invitation (ongoing – ASAP). Responsible: All partners

- WP2-A2: MP to recommend a place for social event and circulate details to partners.

- WP2-A3: AG to circulate email requesting partner approval for Bratislava transport department representatives (1-2 people) to attend General Assembly.

- WP2-A4: Demo sites (excluding Bratislava) to sign and return data protection agreements urgently to enable citizen forum registration survey launch. Responsible: Larissa, Thessaloniki demo site DPOs. Deadline: by 14 November 2025

- WP2-A5: All partners complete competency questions and use cases aligned to ontology requirements. Responsible: All WP2 partners. Deadline: by 10 November 2025

- WP2-A6: Evangelos to send reminder emails to NTUA requesting Delphi expert nominations.

- WP2-A7: Evangelos and Theocharis to coordinate with Larissa to establish reliable communication channel and secure timely WP2 engagement.

- WP2-A8: LS to verify whether ETH Zurich institute plans to participate in Slovakia transport model tender and report findings to Marianna. Responsible:

- WP2-A9: YR to discuss D7.2 deliverable approach with project officer (meeting scheduled Friday morning) and circulate outcome to partners.