Antifragicity

Minutes of the WP2 Meeting

Friday 19 September 2025 - 9:00 – 10:00

- Attendance:

- Yacine Rezgui, Ali Ghoroghi, Evangelos Manthos, Sun Linghang,  Marianna Páleníková, Afrouz Ghaemi, Katerina Moschopoulou, Theocharis Vlachopanagiotis, Anastasia Tzioutziou, Andrei Hodorog, Cyrille Medard De Chardon, Zhaoxing Wang, Alexandros Koimtzoglou

- Meeting Summary

Consortium Agreement (YR):

- Cardiff legal confirmed receipt of AHEPA signatures.

- Cardiff finance preparing first round of SME payments.

D2.1 Deliverable (YR):

- Submitted to EC portal on 29 August; acknowledged by PO.

- Partners reminded not to share until official approval.

Citizen Assemblies (CMD, MP, KM):

- Bratislava: confirmed for 22–24 and 31 January 2026.

- Thessaloniki: expected early January 2026; venue under discussion (university or city hall).

- Larissa: tentative date in December 2025; LV and KM following up with local team.

- Zhytomyr/Odesa: collaboration with Horizon Bridge project finalised; Zhytomyr assemblies to run late October–early November 2025. Odesa’s role will be observer/expert participation.

- Communications: Antonis to finalise outreach material by mid-October. A thematic areas meeting scheduled for next week.

T2.3 Equilibrium Model (AG):

- AG responded the comments/questions from Nancy and Linhang and will present the modified model in the next meeting.

T2.5 Ontology (AFG, ZW, AH):

- Kick-off held on 12 September.

- Ontology design following NEON methodology: competency questions, use cases, modularisation.

- Next steps: partners to propose use cases and competency questions by end of September.

- Protégé project and repository to be set up by AH and AG.

T2.6 Delphi Consultation (YR, AG):

- Launch expected in early November.

- Partners reminded to submit 2–3 expert nominations; so far only 7 received.

- AUTH and DEMO confirmed they will send names by 22 September.

T2.7 KPIs & Dashboard (EM):

- AUTH held first internal meeting.

- Excel template shared with partners to capture indicators and methodologies.

- EM requested partners complete the sheet by end of September.

Literature Reviews (AFG, KM, AG):

- Top-down review (AFG): 35-page draft completed; AG revising. Likely to result in two separate publications (systematic review + complexity).

- Bottom-up review (KM): data extraction continuing; coordination meeting proposed to redistribute workload.

WP4 Methodology (SL):

- LS presented the proposed WP4 methodology, focusing on system dynamics modelling.

- Highlighted that the main limitation is lack of data for calibration and testing.

- Stressed the importance of WP2 outputs (taxonomy, ontology, equilibrium model, Delphi, KPIs) as inputs to WP4.

- WP2 and WP4 teams will coordinate further to align methodological requirements and data needs.

- Action Items:

- WP2-A1: AG to circulate revised equilibrium model (with responses to Nancy and Linghang’s comments) for feedback before the next meeting.

- WP2-A2: LV/KM to finalise dates with Larissa; Antonis to prepare communication material by 30 September.

- WP2-A3: Partners to propose use cases/competency questions for ontology by 10 October.

- WP2-A4: AH/AG to set up Protégé repository and share access.

- WP2-A5: Partners to send 2–3 Delphi expert nominations by 22 September.

- WP2-A6: EM to consolidate KPI/indicator template inputs by end of September.

- WP2-A7: AFG to finalise draft top-down literature review and circulate; KM to share updated bottom-up extraction tables.