Antifragicity

Minutes of the WP2 Meeting

Friday 12 September 2025 - 9:00 – 10:00

- Attendance:

- Yacine Rezgui, Ali Ghoroghi, Evangelos Manthos, Lisa Verhasselt,  Sun Linghang,  Marianna Páleníková, Afrouz Ghaemi, Katerina Moschopoulou, Theocharis Vlachopanagiotis, Natalia Horshkova, Maria Tsami

- Meeting Summary

Literature Reviews (AFG, KM, AG):

- Top-down (AFG): draft 35-page review completed; That will be reviewed internally and submitted at the end of September.

- Bottom-up (KM): draft writing has begun, and a meeting will be scheduled with the other teams.

- Ali will start writing a paper from the findings of D2.1

T2.1 Deliverable(YR)

- D2.1 confirmed submitted to the EC’s SIGMA portal.

T2.2 Citizen Assemblies (LV)

- Larissa: date agreed — first weekend of December 2025; all three processes (Larissa, Bratislava, Thessaloniki) now scheduled before the extended end-February deadline.

- Odesa/Bridge collaboration (Zhytomyr): collaboration terms finalised; awaiting Natalia’s confirmation of participants (civil administration/experts). Reimbursement will cover travel & accommodation only (no speaker fees).

- Comms: all demo sites responded to the Doodle; Lisa to confirm the communications meeting with Antonis. Target to start public outreach mid-October.

T2.3 Equilibrium Model (AG)

- Follow-up to the technical discussion (feedback from Yacine, Maria and Theocharis).

- Core concept: performance-tracking with convergence dynamics toward a target antifragility factor (illustrative +10% improvement; pilot-specific).

- Behavioural/social baselines to be incorporated (links to social indicators and assembly insights).

- Resume discussion Friday 28 September. Deliverable due end of October.

T2.5 Ontology (AFG)

- Kick-off today 16:00 CET. Aim: machine-readable ontology of urban events (NEON methodology), modelling environmental factors, traffic events, and infrastructure states to support analysis and scalability.

T2.6 Delphi Requirements (YR/AG)

- Expert recruitment ongoing: 7 names so far; Evangelos to send AUTH nominations by Monday.

- Reminder: Delphi will validate the initial consortium requirements before WP5 specification.

T2.7 KPIs & Dashboard (EM)

- First task meeting the week after next; Excel template circulated for partners to provide indicators, methods, project findings (also feeding WP3).

- WP3 work has begun in parallel.

Consortium Agreement / Payments

- AHEPA has now signed as required; payments expected imminently following Cardiff legal processing.

- Action Items:

- WP2-A1: LV to confirm communications meeting date with Antonis; begin outreach planning for mid-October.

- WP2-A2: Natalia to confirm Odesa/Bridge collaboration details (participants; travel/accommodation basis).

- WP2-A3: AG to circulate revised equilibrium model and written replies to comments by next weeks; schedule schedule/open Friday, technical session to all interested partners.

- WP2-A4: AFG to host T2.5 ontology kick-off today and share slides/decisions afterward.

- WP2-A5: All partners to submit 2–3 Delphi expert nominations (AUTH to send by Monday).

- WP2-A6: EM to schedule T2.7 meeting for the week after next; partners to complete the KPI/indicators Excel.

- WP2-A7: YR/AG to keep partners informed on payment release timing once notified by Cardiff finance/legal.