Antifragicity

Minutes of the WP2 Meeting

Friday 5 September 2025 - 9:00 – 10:00

- Attendance:

- Yacine Rezgui, Ali Ghoroghi, Zhaoxing Wang, Evangelos Manthos, Lisa Verhasselt,  Sun Linghang,  Marianna Páleníková,  Afrouz Ghaemi, Katerina Moschopoulou,  Theocharis Vlachopanagiotis, Katerina Moschopoulou, Natalia Horshkova

- Meeting Summary

Consortium Agreement and Payments (YR, TV, EM, AG):

- Cardiff legal team still awaiting a formal response from AHEPA on the consortium agreement. Evangelos will call AHEPA directly.

- AG will circulate the document received from AHEPA to Evangelos and Theocharis for clarification.

D2.1 Deliverable (YR, AG):

- Submitted successfully at the end of August; available on SharePoint.

- To remain internal until approved by the Project Officer before being made public.

Citizen Assemblies (LV):

- Bratislava: Venues confirmed for 22–24 and 31 January 2026. Participant registration survey led by Bratislava team; sortition in December. Facilitators confirmed. Remuneration process pending.

- Thessaloniki: Targeting early January; venue under discussion (university or City Hall). Registration survey led by university; sortition by Liser. Dates and venue confirmation pending.

- Larissa: No contact; Lisa will reach out again. Katerina will also try by phone.

- Odessa/Zhytomyr: Collaboration agreed with Horizon project Bridge; Zhytomyr assemblies set for 25–26 October and 1–2 November 2025. Odessa may send experts/administrators to participate. Confirmation from Natalia still pending.

- Next steps: communication strategy, outreach by mid-October, thematic areas meeting next week, facilitation training (mid-November), expert selection (December).

T2.3 Equilibrium Model (AG):

- Draft models A–C presented. Model A: simple, KPI-based, suitable for D2.3 deliverable. Model B: intermediate detail, potential for publication. Model C: highly complex, requires assumptions and simulation, mainly for academic output.

- Meeting scheduled with ETH Zurich (SL) next week; other partners welcome to join.

- Model A can be instantiated per pilot site. Deliverable due end of October.

T2.4 Survey (LV):

- No major changes; framework depends on thematic areas and assembly outputs.

T2.5 Ontology (AFG):

- Kick-off meeting set for Friday 12 September, 13:00–14:00 CET. Aim: machine-readable ontology of urban events, using NEON methodology, linking environmental, traffic, and infrastructure factors. Deliverable due end of January 2026.

T2.6 Delphi Consultation (YR, AG):

- Requirements to feed into WP5. First internal requirements draft expected by January–February. Delphi rounds to start by early November at the latest.

- Partners asked to nominate 2–3 experts; only seven experts proposed so far.

T2.7 KPIs and Dashboard (EM):

- Internal AUTH meeting planned next week.

- Excel template circulated to partners to collect project findings, indicators, and methodologies supporting WP3 and WP4.

- Task will draw data from T2.3 and the literature reviews.

Literature Reviews (AG, AFG, KM, LV):

- Top-down (AFG): draft 35-page review completed; AG to revise within a week. Likely to produce two separate papers. Candidate journals being identified (e.g., Total Science of business Environment).

- Bottom-up (KM): LV suggested resuming coordination meetings to share the load.

WP3 and WP4 (EM, SL):

- WP3 progressing; awaiting more input on Excel. Meeting planned soon.

- WP4 to start in two weeks; preparatory work ongoing.

Survey Results (AG):

- 154 responses collected; 140 used in D2.1.

- Questionnaire will remain open to support future work and potential publications.

- Dataset is SPSS-ready and can be shared with interested partners.

- Action Items:

- WP2-A1: EM to call AHEPA to resolve consortium agreement issue; AG to forward latest document for review.

- WP2-A2: AG to keep D2.1 on SharePoint until PO approval.

- WP2-A3: LV to share slides and follow up with Larissa; KM to call Larissa. Natalia to confirm Zhytomyr collaboration.

- WP2-A4: LV to initiate communications outreach meeting next week; thematic areas to be finalised.

- WP2-A5: LV/Liser to organise facilitation training (mid-November).

- WP2-A6: AG to share equilibrium models with partners (meeting next Thursday) and invite partners.

- WP2-A7: AFG to hold ontology kick-off meeting 12 September.

- WP2-A8: Partners to submit 2–3 expert nominations for Delphi panel (still only 7 received).

- WP2-A9: EM to lead AUTH internal meeting on T2.7 and update partners next week.