Antifragicity

Minutes of the WP2 Meeting

Friday 3 October 2025 - 13:00 – 14:00

- Attendance:

- Yacine Rezgui, Afrouz Ghaemi, Ali Ghoroghi, Anastasia Tzioutziou, Cyrille Medard De Chardon, Evangelos Manthos, Lisa Verhasselt, Makridis Michail, Maria Tsami, Sun Linhang, Tania Demirtzioglou, Yacine Rezgui, George Mitsinikolis, Fotini Kehagia.

- Meeting Summary

T2.1 Status

- AG is translating outputs into a journal paper.

T2.2 Citizen Assemblies (LV)

- Dates: Larissa early December 2025; Thessaloniki early January 2026; Bratislava late January 2026. Thessaloniki venue preference: City Hall; final confirmation in ~15 days.

- Outreach & website: Site “ready in ~2 weeks”; outreach latest 20 Oct; partners to translate website content; public input features planned (bi-directional website).

- Operations: Liser to handle sortition, agenda, facilitator training first half of Nov; partner input sought on thematic areas; experts to be selected per site; registration survey translation pending for GR.

T2.3 Equilibrium Model (AG)

- Revised 3-layer model: (i) traffic equilibrium; (ii) modal equilibrium; (iii) combined infrastructure & supply-side. Introduces antifragility “gate”, positive/negative KPI sets, and System Response Index (SRI) with short/long-term learning.

- Draft circulated to peers; AG to incorporate feedback Mon/Tue and send to official reviewers by 7-10 Oct; fuller presentation next week. YR notes publication potential (e.g., proceedings).

T2.4 Social Acceptability Survey (CMDC)

- EU-wide survey (EU Survey tool preferred; local institute approval pending). Framework finalised in Nov; launch Feb, close Apr; press-release–led sampling in partner countries. To integrate citizen-assembly outputs and align with model-feasible policy levers; joint session with T2.2 planned.

T2.5 Ontology (AFG)

- IDEF0 process prepared; requirements template to partners (target was 6 Oct, extend for broader input). Requirements must be user-centred (not only technical); involve Liser/partners. After capture + literature corroboration → Delphi to firm requirements.

T2.6 Delphi (AG)

- ~10 expert names collected; partners asked to send 3–4 nominees each; plan for 3 rounds aiming at consensus on requirements.

T2.7 KPIs & Dashboard (AT)

- Three subtasks: (1) requirements + KPI definition (literature & expert survey); (2) KPI catalogue with metrics mapping quantitative & qualitative inputs (incl. social media, acceptability); (3) application framework integrated with LCA, validated for applicability & EU-standards compliance. Links to T2.1–T2.5 and feeds WP3–WP6.

- Discussion: strengthen linkage to T2.3 variables (equality, etc.); YR suggests consulting SCIS KPIs and exploring a dynamic dashboard (implementation likely in WP5).

WP3 Overview (MT)

- Active tasks: 3.1 (transport network & land-use dynamics) and 3.2 (participatory vulnerability analysis). Excel template circulated for partner inputs; deadline 10 Oct. 3.1 runs M4–M10 with draft framework to partners M7–M8; WP3 outputs will inform WP4.

WP7 Clarification (TD)

- D7.2 due date appears before WP7 start in DoA; YR to contact Project Officer to correct; Tania to email suggested new date.

- Action Items:

- WP2-A1 (T2.2): LV/CMDC to email partners the final thematic areas and request feedback; confirm Thessaloniki venue and facilitator-training date (early Nov).

- WP2-A2 (T2.2): Antonis + demo sites to finalise website and translations; begin public outreach by 20 Oct.

- WP2-A3 (T2.3): AG to incorporate peer feedback by Mon/Tue and circulate review version by 7-10 Oct; present details next week.

- WP2-A4 (T2.4): CMDC to schedule joint T2.2–T2.4 session on scenarios/levers; progress EU Survey approvals; plan press releases.

- WP2-A5 (T2.5): AFG to circulate requirements template (extended timeline) and organise review; ensure user-centric capture.

- WP2-A6 (T2.6): All partners to submit 3–4 Delphi expert nominations (target list ~20); AG/YR to plan 3-round process.

- WP2-A7 (T2.7): AUTH to align KPI set with T2.3 variables and check SCIS KPIs; consider dashboard pathway with WP5.

- WP3-A1: Partners to complete WP3 Excel by 10 Oct; WP3 to circulate draft conceptual framework M7–M8 for feedback.

- WP7-A1: YR to contact PO re D7.2 date correction; TD to email proposed schedule.